## Overview
StyleMint Mobile — Team Work Tracker
API integration backlog by owner · status from a code audit of the dev branch · 6 July 2026
Workflow: Not started → In progress → In review (Smit) → In QA → Completed. 'Blocked' = built, waiting on backend.
Person | Owns | Items | Not started | In progress | Blocked | In review | In QA | Completed | Parked
Cilus | Creator flow | 10
Sailesh | Customer flow | 14
Savyata | Vendor flow | 12
Smit | PM / Integration Lead | 6
TOTAL | all roles
What the statuses mean
Not started | Work has not begun. If 'Waiting on = Backend', it can't begin until backend provides the endpoint.
In progress | The developer is actively building it.
Blocked | Built on our side, but stuck waiting on the backend to confirm or add a server endpoint. Not an app-team delay.
In review | Developer finished; awaiting Smit's review before it goes to QA.
In QA | Passed your review and is being tested by QA.
Completed | QA has signed off. This is the ONLY status that counts as truly done.
Parked | Deliberately deferred this cycle by a product decision.
Note: status reflects what is built in the code today. Nothing in the three app flows is 'Completed' yet because none has passed QA — the finished work is sitting at 'In review'. Advance items to In QA / Completed as they clear. 'Waiting on' shows who must act next: Backend, App team (us), Smit (review), or QA.

## Smit
Smit
PM / Integration Lead · task IDs P# · as of 6 Jul 2026
ID | Feature | What this task is | Type of work | Sprint | Status | Waiting on | Where it stands
P3 | Tracking board | Set up a shared tracking board and give every task an ID and an owner. | Coordination | — | Completed | Nothing | This workbook.
P1 | Backend address reconciliation | Run one working session with the backend team to confirm the correct server address for every uncertain endpoint. This single step unblocks ~22 tasks across all three apps. | Coordination | — | In progress | Backend | Several already confirmed & shipped (vendor partnerships, products, KYC); the rest pending.
P4 | Quality gates before merge | Enforce quality on every merge: code must pass the analyzer with zero errors, and each flow is walked through against the live test server. | Coordination | — | In progress | Nothing | Analyzer gate held at 0 errors through every merge; live walk-through sign-off still to be done.
P6 | Daily blocker triage | Run daily check-ins during the busy 'confirm the addresses' phase to clear blockers quickly. | Coordination | — | In progress | Nothing | Ongoing through Sprint 2.
P2 | Raise new-backend requests early | File the three requests for brand-new backend work early (Brand Studio, reel-import search/history, first-run profile signal) because they take longest. | Coordination | — | Not started | Nothing | External action — confirm the tickets are filed.
P5 | Chase notifications bug | Follow up with backend on the empty-inbox login bug affecting notifications. | Coordination | — | In progress | Backend | Notifications wired in the app; confirm the backend bug is closed.

## Cilus
Cilus
Creator flow · task IDs CR# · as of 6 Jul 2026
ID | Feature | What this task is | Type of work | Sprint | Status | Waiting on | Where it stands
CR1 | Analytics dashboard | Connect the creator's analytics screen (profile views, earnings trend, top reels & products) to real server data, replacing the hard-coded sample numbers. | App-side only | Sprint 1 | In review | Smit | Team finished coding — awaiting your review, then QA.
CR3 | Creator profile | Load and save the creator's profile (bio, niche, links) from the server so edits actually persist instead of only living on the phone. | App-side only | Sprint 1 | In review | Smit | Team finished coding — awaiting your review, then QA.
CR4 | Reels list | Give the creator's reels list its own connection to the server (decided it needs its own rather than reusing the customer feed). | App-side only | Sprint 1 | In review | Smit | Team finished coding — awaiting your review, then QA.
CR9 | Tips: history & balance | Show the creator's tip history and current tip balance from the server. | Needs backend path | Sprint 2 | Blocked | Backend | Built our side; tips history/balance server addresses not confirmed.
CR2 | Help & support | Connect the support screen so creators can view and raise help tickets. The screen exists but isn't wired to anything yet. | App-side only | Sprint 1 | Not started | App team | Our team can start now — no backend dependency.
CR5 | Sign-up: ID upload | Let applicants upload identity documents during creator sign-up. | Needs backend path | Sprint 2 | Not started | Backend | Can't start until the upload address exists in the backend spec.
CR6 | Payout methods | Let creators view and add payout methods (bank / e-wallet). | Needs backend path | Sprint 2 | Not started | Backend | Waiting on the correct payout-methods address.
CR7 | Active partnerships | Show only the creator's currently-active brand partnerships. | Needs backend path | Sprint 2 | Not started | Backend | Needs a dedicated endpoint or status filter from backend.
CR8 | Reel studio: delete draft | Let creators delete a saved reel draft. | Needs backend path | Sprint 2 | Not started | Backend | Delete address doesn't match what the server offers.
CR10 | Reel import: tag & history | When importing a reel, let creators search products to tag and see their past imports. | Needs new backend | Sprint 3 | Not started | Backend | Needs brand-new backend endpoints.

## Sailesh
Sailesh
Customer flow · task IDs C# · as of 6 Jul 2026
ID | Feature | What this task is | Type of work | Sprint | Status | Waiting on | Where it stands
C1 | My Orders | Switch the orders screens (list, detail, cancel, return) from sample data to the real server so customers see their actual orders. | App-side only | Sprint 1 | In QA | QA | Reviewed by Smit — passed to QA.
C3 | Payment methods | Remove the temporary test data so saved cards load from the server. | App-side only | Sprint 1 | In QA | QA | Reviewed by Smit — passed to QA.
C4 | Saved items | Remove the temporary test data so saved / wishlist items load from the server. | App-side only | Sprint 1 | In QA | QA | Reviewed by Smit — passed to QA.
C5 | Shipping addresses | Remove the temporary test data so addresses load from the server. | App-side only | Sprint 1 | In QA | QA | Reviewed by Smit — passed to QA.
C11 | Notifications inbox | Confirm the notifications inbox points at the correct server address. | Needs backend path | Sprint 2 | In QA | QA | Reviewed by Smit — passed to QA.
C6 | My profile / account | Finish the profile screen: let users upload a profile photo and complete the account-deletion wiring. | App-side only | Sprint 1 | In progress | App team | Account delete done; profile-photo upload still being built.
C7 | Discovery: related & save | Show 'related products' on a product page and let users save an item for later. | Needs backend path | Sprint 2 | Blocked | Backend | Save works; 'related products' address still needs confirming.
C12 | Social: feed, stories, drops | Enable sharing a post, deleting a story, and drop-party invite / QR scan. | Needs backend path | Sprint 2 | Blocked | Backend | Screens built; several server addresses to confirm.
C13 | Social: group cart & co-watch | Enable shared group-cart add/remove and co-watch session details & reactions. | Needs backend path | Sprint 2 | Blocked | Backend | Screens built; server addresses to confirm.
C8 | Product reviews summary | Show a ratings summary (average stars, counts) on product pages. | Needs backend path | Sprint 2 | Not started | Backend | No summary endpoint — decide server-side vs in-app calc.
C9 | App language setting | Save and load the user's chosen language from the server. | Needs backend path | Sprint 2 | Not started | Backend | Language endpoint isn't available.
C10 | Support categories | Load the list of help categories when a customer raises a ticket. | Needs backend path | Sprint 2 | Not started | Backend | Correct address to confirm.
C14 | First-run profile prompt | After login, detect missing mandatory profile info and prompt the user to complete it. | Needs new backend | Sprint 3 | Not started | Backend | Needs a new 'is profile complete?' signal from the server.
C2 | Customer reels feed | Switch the reels feed from sample data to the real server. | Product decision | Parked | Parked | Decision | Deliberately kept on sample data this cycle until the reel pipeline can seed real content.

## Savyata
Savyata
Vendor flow · task IDs V# · as of 6 Jul 2026
ID | Feature | What this task is | Type of work | Sprint | Status | Waiting on | Where it stands
V1 | Customer inquiries | Complete the connection so vendors can see customer product inquiries in-app. | App-side only | Sprint 1 | In review | Smit | Team finished coding — awaiting your review, then QA.
V2 | Analytics dashboard | Connect the vendor analytics screen (sales, revenue, commissions) to live server data. | App-side only | Sprint 1 | In review | Smit | Team finished coding — awaiting your review, then QA.
V3 | Creator performance | Build the connection so vendors can see how their partnered creators are performing. | App-side only | Sprint 1 | In review | Smit | Team finished coding — awaiting your review, then QA.
V5 | Partnerships & campaigns | Point partnership / campaign requests at the correct server addresses so vendors can invite and manage creators. | Needs backend path | Sprint 2 | In review | Smit | Addresses confirmed & remapped — awaiting review, then QA.
V6 | Product management | Fix product view, stock-update and archive to use the correct server addresses. | Needs backend path | Sprint 2 | In review | Smit | Addresses confirmed & corrected — awaiting review, then QA.
V8 | Sign-up: KYC documents | Point KYC document upload and listing at the correct server addresses. | Needs backend path | Sprint 2 | In review | Smit | Addresses confirmed & corrected — awaiting review, then QA.
V7 | Earnings & payouts | Show the vendor earnings ledger and payout methods. | Needs backend path | Sprint 2 | Blocked | Backend | Built our side; ledger & payout addresses still to confirm.
V9 | Matchmaking | Show a creator-vendor compatibility score and let vendors invite matched creators. | Needs backend path | Sprint 2 | Blocked | Backend | Built our side; addresses still to confirm.
V10 | Add product: image upload | Let vendors upload product images when adding a product. | Needs backend path | Sprint 2 | Blocked | Backend | Upload endpoint isn't available yet.
V11 | Order returns | Let vendors process a return on an order. | Needs backend path | Sprint 2 | Blocked | Backend | Return endpoint isn't available yet.
V12 | Brand Studio | Enable campaign templates, campaign analytics and market insights. | Needs new backend | Sprint 3 | Blocked | Backend | Screens built; all three features need new backend endpoints.
V4 | Help & support | Connect the support screen so vendors can view and raise support tickets. The screen exists but isn't wired yet. | App-side only | Sprint 1 | Not started | App team | Our team can start now — no backend dependency.